## Project Deliverables Status
PROJECT NAME | Project Management Lesson Learned Web Application | PROJECT CODE | PMLL | STATUS KEY | BUDGET KEY
PROJECT MANAGER | First and Last | DATE OF STATUS ENTRY | 2021-10-01 08:00 | ROADBLOCK / OVERAGE | OVER
PERIOD COVERED | 09/17/2021 - 10/1/2021 (2 weeks) | PROJECTED DATE OF COMPLETION | 2021-12-06 | POTENTIAL RISKS / DELAYS | ON
|  |  |  | MONITORING CLOSELY | UNDER
PROJECT STATUS THIS WEEK |  |  |  | ON TRACK
OVERALL PROJECT STATUS | ON TRACK | SUMMARY | Regained lost time from last period presented; Previous risk occurance, closed and applied change request plan; Project is back on track; Data Analysis began 1 days earlier than anticipated;Delay in some tasks assigned, but minimal, as time get made up.
MILESTONES | Code Writing Completed (Basebone of this project)
Data Collection Completed (Input needed for upcoming work packages)
PROJECT COMPONENTS
COMPONENT | STATUS | OWNER / TEAM | NOTES
BUDGET | ON | Joel Jacobson | Exceptional work on keeping budget as planned. Original Budget plan can was associated to task during planning phase.
RESOURCES | POTENTIAL RISKS / DELAYS | Joel Jacobson | 1 member working on all remaming tasks in sequential order.
TIMELINE | MONITORING CLOSELY | Joel Jacobson | On track to final launch date
RISKS | ON TRACK | Joel Jacobson | Previous trigger risk has been targets and relief with a system request roboust plan.
SCOPE | ON TRACK | Joel Jacobson | Work Packages on track and no delay
CRITICAL PATH AND CRITICAL TASKS
Task Count | DESCRIPTION | OWNER / TEAM | RECEPTION
12/16 | There is a Critical Path trend of 12 tasks from 16 task | Joel Jacobson | There is no margin error to have at this point of the project. Time it is tight and constraint
Per critiical tasks the team is working closely on saving atleast 8 hours to have a complete day of float to release some critical tasks from its critical path
RISKS AND ROADBLOCKS
RISK NUMBER | DESCRIPTION | OWNER / TEAM | FIX
R5 | Insufficient Data Collection | Joel Jacobson | Scope adjustment, moved into Execution Phase, baseline schedule once change request approved; Republish Survey to target audience; collection by target date of end task.
STAKEHOLDER DELIVERABLES COMPLETED (based on RTM)
CATEGORY | REQUIREMENTS | PRIORITY | ACCEPTANCE CRITERIA
Structural/Security | 4. Database creation with all tables for all data entry for lesson learned | High | At least Insert a full batch of data of a lesson learned (dummy data) during Testing Phase
Functional/Security | 9. Code Writeup for the Web Application | High | Free of Errors on Web Application and perform all components successful.
Data inserted for demonstration during Accptance Criteria Survey Report. G - Completed, Y - Partial, R - Risk Occured
SYSTEM CHANGE REQUESTS COMPLETED
WBS | Category | Change Request | Requested by
3.1.5 3.1.6SCR: Exec#1 | Execution Phase | Project Schedule / Project Scope | Joel Jacobson
HIGHLIGHTS AND KEY TAKEAWAYS
Project Team Member need to follow all details and capture in lesson logs as well in change logs pages.
Revision dates and revision numbers need to be updated side by side of other projects files for matching data.
UPCOMING PLANNED ACTIVITIES (week# based on last project deliverables status update date)
WEEK NUMBER | STATUS | DETAILS
1 | ON TRACK | Layout Creation, and Completion for Req. Traceability Matrix ID# 5 for acceptance Criteria
2 | ON TRACK | Status Report for Milestone #3 October 15,2021
1-3 | MONITORING CLOSELY | Next PPM#3 Deliverables to be track and completed.
3 | MONITORING CLOSELY | Initiation of Application Troubleshooting Section in 3/4 in the execution phase.
OVERALL PROJECT PROGRESS TIMELINE (EXECUTION - CLOSEOUT PHASES) BIG PICTURE
Project Buffer 1% of Project Duration
MILESTONE 2
Data Collection and Research completed
MILESTONE 3
Research Paper and Application COde Reviewed by SME
MILESTONE 4
Testing Phase of Web Application Successfull by all Critical Success Factors from RTM
MILESTONE 5
Closeout of Project; consolidate Documentation and Present Project Results
CURRENT TIMELINE POSITION
10/1/2021
ROADBLOCK 1
R5: SCR #1 Insufficient Research Collected Data
PROJECT START DATE
08/15/2021
PROJECT END DATE
12/6/2021