## Slide 1
1
Overall Project Progress Status Report
Project Management Lesson Learned Web Application
2nd/Oct/21
Overall Status:
Key Discussion Areas:
Time Management Incorporate Lesson Learned Plan for possible changes in some tasks and delegation.
Project Milestones: | Target: | Expected completion | Status
Code Writing | 28/Sep/21 | 28/Sep/21 | 
Data Research Analysis | 2/Oct/21 | 2/Oct/21 | 
Layout Design | 15/Oct/21 | 15/Oct/21 | 
Security Implementation | 19/Oct/21 | 18/Oct/21 | 
Testing | 26/Oct/21 | 25/Oct/21 | 
User Manuals | 29/Oct/21 | 28-29/Oct/21 | 
Lesson Learned | 13/Nov/21 | 13/Nov/21 | 
Project Closeout | 4/Dec/21 | 30/Nov/21 | 
Project Final Report | 6/Dec/21 | 4-5/Dec/21 | 
Per 3-weeks Summary:
Completed PPM1 Deliverables: 100% - 9/9 Completed PPM2 Deliverables: 100% - 9/9 In-Progress PPM2: Project Status Report Dashboard:20% - 0/1 Not Started PPM3 Deliverables: 0% - 5/5 System Req. Analysis from change request: Completed In-Progress Inputs Research Paper: 25% (Approx. 10 pages)
Look Ahead [two weeks]:
Plan on PPM3 Deliverables and seek assistance for verification on the right path per task. Continue working on Research Analysis Paper for the Project. Update all my requirements documents for the project
Realized Risks / Change Management:
System Change Request to incorporate Data Collection Analysis into Plan Schedule. Working independently. Consistency on all area of tools utilizations (ex. Excel, Power Point, Word, Projects, etc.) with same values and results to keep clean and neat template uniformity
Constraints Identified:
Time Utilization during 4:10 hrs of gathering and working with the project per weekday Budget burnout as planned
Project Metrics | Status
Budget | 
Schedule | G
Risk Management | 
Constraints | 
S
G
G
Legend: Issues Satisfactory Excellent Completed Incomplete
R
S
I
S
I
I
✔
G
I
S
I
✔
✔
PMLL
I
I
I
Notes: Key tasks completed and key tasks started.
PPM1 Deliverables:
Stakeholder Identification and Analysis ✓
Project Charter (1) ✓
Preliminary project schedule (2) ✓
Preliminary WBS ✓
200-word Project Abstract (3) ✓
Letter(s) of support from project sponsor ✓
Preliminary GSP ✓
Knowledge Area Selection and measures ✓
Preliminary narrative description of how project will contribute to PM body of knowledge (i.e., expected project outcomes and processes uniquely applied.) (0) ✓
PPM Deliverables: (#2)
Project Scope statement ✓
Table of content for PM Plan and Final Project Report ✓
Signed Student/Advisory Committee “contract” ✓
Research Sources and Key Words O
Preliminary research methods and approach to analysis (e.g., surveys, interview questions, statistical analysis, etc.) O
✓ = Completed
O = In Progress

## Slide 2
Project Schedule Timeline
Tasks Summary: based on hrs and 10 min per weekdays (Mon – Fri) Execution, Cont.&Mon. and Closeout Phases |  | 
Task Name | Duration | % Complete
Database Creation | 1.5 days | 100%
Code Writing | 11.25 days | 83%
Data Collection | 1.5 days | 0%
Data Collected Analysis | 1 day | 0%
Layout Creation | 3.38 days | 0%
Hosting/Domain Setup Implementation | 0.75 days | 0%
Security | 1.5 days | 0%
Development | 1.5 days | 0%
Testing | 1.5 days | 0%
Production | 0.75 days | 0%
User Manual | 0.75 days | 0%
Lesson Learned Templates | 0.75 days | 0%
Code Review | 1.13 days | 0%
Project Management | 1.5 days | 0%
Manage Cost | 0.38 days | 0%
Manage Schedule | 1.13 days | 0%
Lessons Learned | 1.5 days | 0%
Archive Project Data | 0.75 days | 0%
Project Closeout Documentation Review | 3.75 days | 0%
Project Final Report | 4 days | 0%
Project Completion | 0.5 days | 0%
Project Name | Duration (days) | Start | Finish | % Complete
PLLWA | 230 | 1/17/21 | 12/6/21 | 63%
Overall Project Progress Status Report
Project Management Lesson Learned Web Application 2nd/Oct/21
PMLL
Project Closeout
Project Mon. & Control
Project Execution